List of Common Programmes
GROUP 1
1. CCE
  1. Creating a forum to share experiences of CCE implementation and lessons thereon.
  2. To help
2. Class IX text books(6th and 9th)
3. ICT – DIET and BRC faculty Development
4. Resource Centres
5. Spoken English and Communication Skills FIP for TEs
6. Class V and VIII TB hardspots
7. Empowerment of BRC and CPR
8. Inputs towards Curriculum design and development

GROUP 2
1. Research Studies
2. Establishment of a tool room(ICT) If given even at the block levels in RMSA, no need here
3. Evaluation Studies on Training programmes
4. Publications
5. Exposure visits
6. Course Material Development
7. Supplementary Material Development
8. Training Management System

DHARWAD , YADGIR, KUMTA - GROUP 3
1. Website
  1. Objectives
    1. To create a website for the DIET using a simple software like wiki, so that the DIET itself can maintain the website. DIETWiki will be used for this purpose, which is a part of Karnatakaeducation.org.in
    2. To enable access for all, the necessary information like,structure,function,staff informatio:n,training programes etc
    3. To provide both static and dynamic information, dynamic information (programs) will be updated once in a quarter
    4. To enable DIET and faculty to share information about their work and development
    6. To share curricular resources with other DIETs

    1. time frame – workshop – May/June, rest of the year for resource update every quarter
  2. Strategy: Training will be conducted at divisional level for selected DIET faculty in installation and use of Wiki.
    Cascade mode will be used training for other DIET faculty within the DIET (support from IT for Change, American India Foundation, Azim Premji Foundation will be taken for all ICT integration programmes)
    -collect the information from all Departments within the DIET.
    - Upload the information to Website.
    -Quarterly updation of information.
  3. Materials: material creation in digital form.(e-resources)
  4. Target coverage: Faculty of DIET,Stake holders, other departments, public at large

  1. Outcomes:Greater awareness about DIET programes,
    interaction between DIET ,BRC,teachers students parents public
    Networking among DIETs,DSERT.
    Creating and sharing resources.
  2. Budget:Rs 0.5 lakh
    1. for training faculty
    2. for digitising information / maintenance

1. Seminars/Conferences/Symposium:
  1. Objectives:- To conduct seminar/symposia/conference regarding topics pertaining to local departments
    - To provide plat form for functionaries to dicsuss and gain insights into necessary issues.
    -
  2. Strategy: Conduct meetings for DIET faculty and plan for conducting seminar/conference/symposium (subject ,date,target, work distribution, resource persons etc)Conducting that programe systematically at DIET level.
    Record the proceedings/decisions taken/conclusions and upload.printing the documents (seminar outputs/papers)and supplied to blocks.
  3. Materials:Human resource,digital resources,good venue with all facilitiesetc.
  4. Target coverage:Supervisory officers at district level/Teacher educators/Primary teachers/Secondary teachers.
  5. Outcomes:Creating awareness about new /locally important issues
    provides insights for planning/policy decisions at district level.
  6. Budget:1.5 lakh
    (rems funds also have funds for seminars. But try to avoid duplication and share resources)
2. On site support for teachers through BRPs and CRPs (indirect approach):

  1. Objectives:
    1. To provide on site support for teachers through BRPs and CRPs (indirect approach).
    2. Understand local issues faced
    3. understand challenges in incorporating workshop learnings
    4. understand school level issues
    5. virtual support through on-line methods (email, phone)
    6. share learnings from other schools/locations with schools
    7. encourage networking amongst teachers
    8. empowerment of brp and crp
  2. Strategy:By formation of groups of subject experts,identification of difficult concepts,visit selected schools.Group would clarify the doubts /guidance to teachers in their difficult areas.
  3. Materials:Human resource,reference materials,
  4. Target coverage:/CRCs/BRPs
  5. Outcomes:onsite support.
  6. Budget:0.5
FDP can have a component of school visits for learning of DIET faculty
SHIFT FROM MONITORING TO SUPPORT MODEL
1. Inclusive education:Gifted children,learning disabilities,udc, physically handicaped,lambani,marginalised sections of the society etc.
  1. Study practices of inclusion and exclusion in the classroom context
  2. provide inputs for pilot programmes
  3. develop sensitivity towards this issue amongst teacher educators

  1. Objectives:To enable the DIET faculty /BRC/CRC to understand the nature and scope of inclusive education
    To conduct research regarding inclusive education
    BRC/IERT capacity building, refer to existing studies conducted by ssa etc
  2. Strategy:,preperation of relevent tool,data collection,
    analysis of DISE data and conducting survey to understand status, on the basis of the status conduct lab area studies. CHILDREN AS AN IMPORTANT PARTICIPANTS IN THE STUDIES AND PILOTS SO THAT THEIR PERSPECTIVES ARE TAKEN INTO ACCOUNT.
    University/experts linkages.
    Documentation and sharing with DIET faculty BRC/CRC and other DIETs.
  3. Materials:DISE REPORTS,Survey tools,technical support.
  4. Target coverage:TE IERT/BRP/CRP/TEACHERS/CHILDREN
  5. Outcomes:better Understand of the situation of inclusive education in the district and plan pilot interventions.
  6. Budget1.75-2l

Geography

  1. Objectives:
    1. To develop teaching learning material for geography in the form of geo kit.To conduct goegraphy symposium for teachers to improve their skill to fecilitate geography learning.
    2. To develop deeper and broader understanding of geography as an important social sciences subject
    4. prepare local geography resource material
    5. map reading
    6. GIS (geography information system) like googlemaps, open street maps to create geographic resources digitally
    7. social geography focus
  3. Strategy:need analysis will be taken up at district level.
    1. Conduct symposium to teachers on the basis of need anlysis gather important information to prepare geokit.
    2. Conducting workshop to prepare the kit with the help of experts
    3. training on GIS/GPS (openstreetmaps)
    4. conduct orientation programe for district/block level faculties to use geo kit.
    5. All curricular resources created will be made available in digital format on KOER (Karnataka Open Educational Resources) wiki which is website for making educational resources available to all Karnataka teachers
    6. record geographic information system using GPS device
    7. upload gis information on openstreetmaps

  1. Materials: digital& human resources.
  2. Target coverage: BRPs/CRPs/selected teachers
  3. Outcomes:capacity enhancement of teachers to facilitate learning.
    Provision of resource support to teachers. ( DIET as resource centre.)
  4. Budget:Rs 2.75 lakh

1. ICT – CURRICULAR RESOURCE CREATION – SUBJECT BASED
  1. Objective:To use ICT as method for mediating teachinglearning
    To access, create and share resource needs.
  2. Strategy:using varied digital methods to create learning resources:
    i. using educational software applications, such as
    1. Maths – Geogebra, Bruch, K Turtle
    2. Languages SCIM - (language typing), K Hangman etc.
    3. Science – STEP (experiments animation), Stars, Stellar etc. (astronomy), Kalzium
    4. Social science - marble
  3. Materials:softwares,internet,computersystem,text books,supporting materials like,source books,dictionaries,wbesites etc.and subject experts.
  4. Target coverage:TEACHER EDUCATORS 6th and 9th (shared with CTE) std.students/teachers.
  5. Outcomes:effective teaching learning process.
    Easy access to curricular resources.
    Enhanced opportunity for Individualised learning.
  6. Budget Rs.3.0 (Rs0.25lakh per subject)

1. LOCAL DEPARTMENT:
  1. Objectives:
    1. to provide space for /flexibility to try out innovations in the idetified local specific department
    2. to build knowledge in that area and enable DIET to become a resource group for that area
  2. Strategy:
    1. to conduct need analysis,survey/research studies
    2. to design and develop materials.
    3. to develop DIET faculty as professionals/experts in identified area
    4. to develop linkages with higher education institutions in that area
    5. to train teachers in that area
    6. to eventually incorporate elements into the school curriculum for the district at appropriate level

in the first year, the focus will be to initiate research studies/surveys in identified area and once the study report is available prepare required curricular resources
  1. Materials
  2. Target coverage
  3. Outcomes
  4. Budget:5 lakh

Department	Activities	Objectives	Target group	Strategy	Materials	Outcomes/Indicators	Time Frame	Budget
Education	CCE: sharing, clarification, review of material
Humanities	Class 6 text books: Preparing supplementary materials, Review (for editing), Identifying hard spots, Plug in points with NCF, 2005
Science	ICT: Integration into curricular areas for TE faculty, Forming TE networks
ELMP	Resource Centres
Language	Spoken English and Communication Skills FIP for TEs
Language, Science and Humanities	Class V and VIII TB hardspots
ELM	Empowerment of BRC and CRP
ELM	Inputs towards Curriculum design and development
All departments	Research Studies
Science	Establishment of a tool room(ICT) If given even at the block levels in RMSA, no need here
All departments	Evaluation Studies on Training programmes
PSTE	Publications
ELM	Exposure visits
Language	Course Material Development
Humanities	Supplementary Material Development
ELM	Training Management System
ELM	Website
PSTE	Seminars/Conferences/Symposium
Education	On site support for teachers
ELM	Inclusive education: Awareness for faculty; Studies
Education	RtE-Awareness of responsibilities and accountability, Discussions on problems and solutions, Implementation Study
Language	Minority languages: Material development, Translation